ICE TASK 3

---
Submission Requirements
Submission Requirements
- Hand in your submission as a PDF document
- If there is a practical component to this activity be show your working out of the solution via specification document and screenshots

---
Question 1
Question 1
Create a WBS using Microsoft project that matches the details below

---
Questions
Questions
Create a Network Diagram that matches the details below

---
Question 2
Question 2
WBS	Task	Duration	Predecessor	Resources	Costs	Resource costs p/h
1	A	3 days	-	Worker 1		Worker 1 – R50
2	B	5 days	-	Worker 2 & 1		Worker 2 – R100
3	C	4 days	B,A	Worker 3		Worker 3 – R80
4	D	6 days	C	Worker 4 & 2		Worker 4 – R50
5	E	2 days	D	Worker 5		Worker 5 – R200
6	F	1 day	D	Worker 6		Worker 6 – R150
7	G	5 days	D	Worker 6 & 4
8	H	3 days	E,F,G	Worker 1